## Sheet1
Backup Items | Backup Mechanism | Task | Effort | ETA | Dependencies
PCRF
parmdb | pc_export.sh in cron | Update/Convert to Linux/Test | 5 days
Rule engine export | pc_export.sh in cron | Update/Convert to Linux/Test
package versions | pc_export.sh in cron | Update/Convert to Linux/Test
rpm -qa
Prov/BPC configs | pc_export.sh in cron | Update/Convert to Linux/Test |  | 17th January 2012 | PCRF Cluster: Available (Work-In-Progress)
DRA/SLF |  |  | 2 days
parmdb | New custom script in cron | Create Script/Test
slf-config.xml | New custom script in cron | Create Script/Test
Corosync config | New custom script in cron | Create Script/Test
Traffix cpf config | New custom script in cron | Create Script/Test
Traffix webui config | New custom script in cron | Create Script/Test
active subscriber partition | New custom script in cron | Create Script/Test
dra-slf-config.xml | New custom script in cron | Create Script/Test
crm configure save /tmp/config.out | New custom script in cron | Create Script/Test |  | 20th January 2012 | DRA: Available
package versions | New custom script in cron | Create Script/Test
SDB |  |  | N/A
DB backup - | RMAN in cron | Add RMAN to cron if not already there | 1 day
/WideSpan/config directory | New custom script in cron | Create Script/Test
package versions | New custom script in cron | Create Script/Test |  | 24th January 2012 | SDB: Available (Work-In-progress)
Oracle scripts | New custom script in cron | Create Script/Test
BMS |  |  | 2 days
parmdb | New custom script in cron | Create Script/Test
postgress DB | run_pg_backup.sh | Test
Configuration files | New custom script in cron | Create Script/Test |  | 26th January 2012 | BMS: Available (Work-In-Progress)
package versions | New custom script in cron | Create Script/Test
CTA |  |  | ½ day
parmdb | New custom script in cron | Create Script/Test |  | 27th January 2012 | CTA: Availability TBD
package version | New custom script in cron | Create Script/Test
System |  |  | 1 day
IP routing/hosts | New custom script in cron | Create Script/Test
OS | Golden ISO image | Store on BMS
snmp | New custom script in cron | Create Script/Test
syslog | New custom script in cron | Create Script/Test |  | 30th January 2012 | Any System available
/etc/ Directory configs including: bonding configs /etc/sysconfig/network.scripts/ifcfg* /etc/sysconfig/network /etc/modprobe.conf /etc/hosts /etc/sysconfig/network.scripts/*route* /etc/syslog.conf /et/passwd /etc/group /etc/shadow | New custom script in cron | Create Script/Test
Switch (4X BNT/2x G8052 switches) |  |  | 1 day
Configuration | Script scp commands in cron | Create Script/Test
Image | Script scp commands in cron | Create Script/Test |  | 31st January 2012 | Switch: Availablility TBD
Boot | Script scp commands in cron | Create Script/Test